## Action_Plan
Action_ID | NADCAP_Clause | Requirement_Description | Priority | Current_Coverage | Gap_Identified | Recommended_Action | Timeline_Days | Due_Date | Estimated_Cost | Resource_Requirements | Success_Criteria | Risk_Level | Existing_Documents | Implementation_Status
1 |  | Is there a drawing/sketch defining the location of each process line for | Low | No | PARTIAL | Develop supporting documentation to address requirement | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low |  | PLANNED
2 |  | Has the Auditee identified what chemical process scope data shall be | High | Yes | PARTIAL | Review existing documentation to ensure full compliance | 30 | 2025-09-27 | $5,000-15,000 | Senior Engineer + Documentation Specialist | 100% Documentation Complete & Audit Ready | High | Unknown | PLANNED
3 |  | rejects/complaints, key characteristics, 1st pass yield and process capability data. Is there eviden... | Low | No | PARTIAL | Develop supporting documentation to address requirement | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low |  | PLANNED
4 |  | be control charts, pareto charts, management presentations, project summaries or other presentation ... | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown | PLANNED
5 |  | Are inspection and test personnel trained in procedures and techniques | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown | PLANNED
6 |  | the sampling plan to use. If used, are Auditee developed sampling plans available for review and | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown | PLANNED
7 |  | processing the part including masking, blasting, de-masking etc. Has the competency for all personne... | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown | PLANNED
8 |  | chemical process requirements been defined, including processing personnel, testing/inspection perso... | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown | PLANNED
9 |  | other actions were taken to achieve the necessary competence? Is there evidence that the effectivene... | Low | No | PARTIAL | Develop supporting documentation to address requirement | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low |  | PLANNED
10 |  | evaluated? Does the Auditee define and operate a system to ensure competencies | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown | PLANNED
11 |  | are maintained? Have operations/tasks that affect conformity to chemical process | Low | No | PARTIAL | Develop supporting documentation to address requirement | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low |  | PLANNED
12 |  | Does shop paper/traveler, which accompanies each lot, contain as a minimum the following information... | High | No | PARTIAL | Develop supporting documentation to address requirement | 30 | 2025-09-27 | $5,000-15,000 | Senior Engineer + Documentation Specialist | 100% Documentation Complete & Audit Ready | High |  | PLANNED
13 |  | Operations defined by the customer as non-critical or non-technical may be exempt from approval requ... | High | No | PARTIAL | Develop supporting documentation to address requirement | 30 | 2025-09-27 | $5,000-15,000 | Senior Engineer + Documentation Specialist | 100% Documentation Complete & Audit Ready | High |  | PLANNED
14 |  | contract number, but must have traceability to it, or to the engineering requirements. Part identifi... | High | No | PARTIAL | Develop supporting documentation to address requirement | 30 | 2025-09-27 | $5,000-15,000 | Senior Engineer + Documentation Specialist | 100% Documentation Complete & Audit Ready | High |  | PLANNED
15 |  | traveler unless one of the following applies: it does not influence the process steps/sequence; when... | High | Yes | PARTIAL | Review existing documentation to ensure full compliance | 30 | 2025-09-27 | $5,000-15,000 | Senior Engineer + Documentation Specialist | 100% Documentation Complete & Audit Ready | High | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
16 |  | jobs audited. Type may be substituted by material and size. Reference to a defined Test Piece, e.g. ... | High | Yes | PARTIAL | Review existing documentation to ensure full compliance | 30 | 2025-09-27 | $5,000-15,000 | Senior Engineer + Documentation Specialist | 100% Documentation Complete & Audit Ready | High | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
17 | 3.6.1.5.1 | controlled process parameters/ranges and referencing applicable internal process/or inspection proce... | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
18 | 3.6.1.5.1 | departments. 3.6.1.5.2 Pre-process cleaning method(s)? | Low | No | PARTIAL | Develop supporting documentation to address requirement | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low |  | PLANNED
19 | 3.6.1.5.3 | audited. Preprocess cleaning is cleaning of incoming parts prior to the primary process i.e. prior t... | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown | PLANNED
20 | 3.6.1.5.3 | audited. 3.6.1.5.4 Masking? | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown | PLANNED
21 | 3.6.1.5.4 | audited. 3.6.1.5.5 Fixturing, racking? | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown | PLANNED
22 | 3.6.1.5.6 | audited. Shop paper to reference internal racking instruction, a general instruction for routine rac... | High | Yes | PARTIAL | Review existing documentation to ensure full compliance | 30 | 2025-09-27 | $5,000-15,000 | Senior Engineer + Documentation Specialist | 100% Documentation Complete & Audit Ready | High | Unknown | PLANNED
23 | 3.6.1.5.6 | audited or for barrel plating and automated lines. 3.6.1.5.7 Activation (e.g. deoxidation, acid clea... | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown | PLANNED
24 | 3.6.1.5.8 | audited. 3.6.1.5.8 Strike? | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown | PLANNED
25 | 3.6.1.5.9 | Chemical finishing e.g. Plate, anodizing, conversion coating, | Low | No | PARTIAL | Develop supporting documentation to address requirement | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low |  | PLANNED
26 | 3.6.1.5.10 | conversion coating and painting. 3.6.1.5.10 Post-process steps including cleaning, de-masking and re... | Low | No | PARTIAL | Develop supporting documentation to address requirement | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low |  | PLANNED
27 | 3.6.1.5.11 | audited. 3.6.1.5.11 Post-finishing thermal treatment? | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown | PLANNED
28 | 3.6.1.5.11 | audited. 3.6.1.5.12 In-process and final tests and inspections? | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
29 | 3.6.1.5.12 | Final Inspection? | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown | PLANNED
30 | 3.6.1.5.14 | and possibly a final visual look at the parts. It is not a formal lot test or visual inspection step... | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
31 | 3.6.1.5.15 | Documentation of rework that is traceable to the shop paper / traveler | Low | No | PARTIAL | Develop supporting documentation to address requirement | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low |  | PLANNED
32 |  | Do buy-off steps comply with AC7108 Appendix E, and were they | Low | No | PARTIAL | Develop supporting documentation to address requirement | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low |  | PLANNED
33 |  | properly bought off and dated? Are all process parameters defined in AC7108 App D recorded for each | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown | PLANNED
34 |  | the process parameters need not be recorded. Lot inspection and test results are recorded and bought... | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
35 |  | being modified question) Is there a procedure defining system/requirements for process and | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
36 |  | quality planning which effectively ensures compliance with customer and/or specification requirement... | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown | PLANNED
37 |  | or any other personnel, when a discrepancy is detected? Is there a Process Control Document (PCD) fo... | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
38 | 3.7.3.1.1 | defines operations and controls to ensure compliance with applicable specifications and repeatable e... | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown | PLANNED
39 | 3.7.3.1.1 | Composition of all materials to be used, including allowable solution | Low | No | PARTIAL | Develop supporting documentation to address requirement | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low |  | PLANNED
40 | 3.7.3.1.2 | Description of allowable ranges for applicable process parameters for | Low | No | PARTIAL | Develop supporting documentation to address requirement | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low |  | PLANNED
41 |  | PCD must comply with applicable specification or customer requirements. The traveler may define tigh... | High | Yes | PARTIAL | Review existing documentation to ensure full compliance | 30 | 2025-09-27 | $5,000-15,000 | Senior Engineer + Documentation Specialist | 100% Documentation Complete & Audit Ready | High | Unknown; Unknown; Unknown | PLANNED
42 |  | Are jobs processed to the specification revision defined on the | Low | No | PARTIAL | Develop supporting documentation to address requirement | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low |  | PLANNED
43 |  | Are all sub-tier suppliers that provide any consumable material, or | Low | No | PARTIAL | Develop supporting documentation to address requirement | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low |  | PLANNED
44 |  | service used in the process, taken from an approved supplier list? Are all solution analysis and pro... | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
45 |  | Does the processor obtain through customer-provided information: part | Low | No | PARTIAL | Develop supporting documentation to address requirement | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low |  | PLANNED
46 |  | Does the system provide for holding and segregation of hardware | Low | No | PARTIAL | Develop supporting documentation to address requirement | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low |  | PLANNED
47 |  | pending receipt of proper material documentation or if nonconformance is detected? Does the Auditee ... | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown | PLANNED
48 |  | Are actual as-received dimensions for jobs having post-processing | Low | No | PARTIAL | Develop supporting documentation to address requirement | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low |  | PLANNED
49 |  | are not contractually required. Actual pre-process dimensions may be provided by earlier machining i... | High | Yes | PARTIAL | Review existing documentation to ensure full compliance | 30 | 2025-09-27 | $5,000-15,000 | Senior Engineer + Documentation Specialist | 100% Documentation Complete & Audit Ready | High | Unknown; Unknown; Unknown; Unknown | PLANNED
50 |  | Are the company’s facilities clean, uncluttered, and well lighted? | Low | No | PARTIAL | Develop supporting documentation to address requirement | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low |  | PLANNED
51 |  | Are incompatible materials such as acids/alkalis or oxidizers/organics | Low | No | PARTIAL | Develop supporting documentation to address requirement | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low |  | PLANNED
52 |  | segregated in storage? Are materials used in the processing and testing of parts clearly | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
53 |  | production materials. Are materials used in the processing and testing of parts stored to | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
54 |  | preclude damage or degradation from heat, cold, water, atmospheric moisture or other environmental c... | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
55 |  | Does training or a procedure address cleaning of pumps and other | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
56 |  | Is there a policy to ensure that customers are informed of discrepancies | Low | No | PARTIAL | Develop supporting documentation to address requirement | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low |  | PLANNED
57 |  | affecting hardware? (i.e. out of tolerance conditions) Is rework approved by the customer when requi... | High | No | PARTIAL | Develop supporting documentation to address requirement | 30 | 2025-09-27 | $5,000-15,000 | Senior Engineer + Documentation Specialist | 100% Documentation Complete & Audit Ready | High |  | PLANNED
58 |  | for rework approval or where no rework was observed in the audit. Is there a rework procedure that r... | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
59 |  | Is repair/MRB always approved by the customer? | Low | No | PARTIAL | Develop supporting documentation to address requirement | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low |  | PLANNED
60 |  | Is there a procedure to provide for the protection of parts after final | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
61 |  | inspection and during shipment that includes customer requirements? Do shipping documents conform to... | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown | PLANNED
62 |  | in the appropriate part of this Audit Criteria and slash sheets. To check NO to any of the questions... | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown | PLANNED
63 |  | process? All test and inspection equipment, including measurement standards, | Low | No | PARTIAL | Develop supporting documentation to address requirement | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low |  | PLANNED
64 |  | used to accept product or control a process? Does the frequency of recalibration/reverification of e... | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
65 |  | Except for instruments used to control or record time, does the | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
66 |  | calibration cover the range of use and the required instrument accuracy? For instruments used to con... | High | Yes | PARTIAL | Review existing documentation to ensure full compliance | 30 | 2025-09-27 | $5,000-15,000 | Senior Engineer + Documentation Specialist | 100% Documentation Complete & Audit Ready | High | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
67 |  | accordance with the relevant section of AC7108/4 Appendix B. Where Appendix B does not have an appli... | High | Yes | PARTIAL | Review existing documentation to ensure full compliance | 30 | 2025-09-27 | $5,000-15,000 | Senior Engineer + Documentation Specialist | 100% Documentation Complete & Audit Ready | High | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
68 |  | the method defined by the process/test specification and correctly dispositioned? Was the sample siz... | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
69 |  | process/test specification? If test pieces were used for lot testing, were they of the correct mater... | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
70 |  | Periodic testing shall be audited in accordance with the relevant section of AC7108/4 Appendix B. Wh... | High | Yes | PARTIAL | Review existing documentation to ensure full compliance | 30 | 2025-09-27 | $5,000-15,000 | Senior Engineer + Documentation Specialist | 100% Documentation Complete & Audit Ready | High | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
71 |  | with the method defined by the process/test specification and correctly dispositioned? Are periodic ... | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
72 |  | to review and buy-off the test results. Was the quantity of test pieces used for periodic testing in... | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
73 |  | with the process/test specification? Were test pieces used for periodic testing of the correct mater... | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
74 |  | testing. Were the periodic tests (both internal and external) reviewed in the | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
75 |  | requirements for periodic tests where the frequency is not defined by the industry specifications an... | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
76 |  | must be available monthly. The Auditee must not retain processed test pieces for several periods and... | High | Yes | PARTIAL | Review existing documentation to ensure full compliance | 30 | 2025-09-27 | $5,000-15,000 | Senior Engineer + Documentation Specialist | 100% Documentation Complete & Audit Ready | High | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
77 |  | both shop travelers and certification/test report and would they enable the Auditee to reconstruct t... | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown | PLANNED
78 |  | they are readily available for review? Are periodic test results graphed or tabulated, examined for ... | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
79 |  | specifications within the scope of the audit. Are material certifications, manufacturer’s labels, or... | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown | PLANNED
80 |  | Are test pieces traceable to material from which they are made? | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
81 |  | Test pieces used for lot thickness testing do not require traceability. Are test pieces positively i... | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
82 |  | identification that can be traced back to the router/traveler. Test pieces do not need to be identif... | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
83 |  | pieces. Is there documentation which provides for tracking and accountability of | Low | No | PARTIAL | Develop supporting documentation to address requirement | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low |  | PLANNED
84 |  | Is there specific shop paperwork (router, etc.) which is traceable to the | Low | No | PARTIAL | Develop supporting documentation to address requirement | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low |  | PLANNED
85 |  | test pieces which specifies how they are to be processed and which tank they are processed in? Unles... | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
86 |  | NOTE: This section does not apply to solution analysis. Does the Auditee have a documented procedure... | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
87 |  | of procedure. Definitions for "Invalid Test", “Replacement Test” and “Retest”? | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
88 |  | The need for an investigation to determine if the test failure is “Invalid”? | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
89 |  | The requirement that a replacement test is only performed when the | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
90 |  | test failure is conclusively shown, and documented, to be “Invalid”? The requirement that a retest i... | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
91 |  | customer or specification? The requirement that the original test failures, replacement tests, | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
92 |  | nonconforming tests, and retests are logged and cross indexed, including explanations with entries s... | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
93 |  | Are replacement tests performed only when original failed test has | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
94 |  | Are original test failures, replacement tests, retests and validated test | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
95 |  | failures logged and cross indexed, including explanations with entries signed off by authorized pers... | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
96 |  | Is there a procedure which addresses the following in the event of a | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
97 |  | validated testing failure: Immediate notification of all affected customers? | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
98 |  | and typically within 3 working days Identification of all affected hardware shipped to the customer? | Low | No | PARTIAL | Develop supporting documentation to address requirement | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low |  | PLANNED
99 |  | Segregation of all affected in-house hardware? | Low | No | PARTIAL | Develop supporting documentation to address requirement | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low |  | PLANNED
100 |  | Immediate shutdown of the affected process/process line pending | Low | No | PARTIAL | Develop supporting documentation to address requirement | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low |  | PLANNED
101 |  | resolution? Investigation of failure cause and implementation of corrective action? | Low | No | PARTIAL | Develop supporting documentation to address requirement | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low |  | PLANNED
102 |  | After the process has been corrected is it tested to show compliance to | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
103 |  | test results being obtained if the customer agrees to "at risk" release or parts are held at the Aud... | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
104 |  | Are there assigned responsibilities for review and approval of analysis | Low | No | PARTIAL | Develop supporting documentation to address requirement | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low |  | PLANNED
105 |  | results, authorization of re-analysis, calculation of process solution additions and corrections, an... | High | Yes | PARTIAL | Review existing documentation to ensure full compliance | 30 | 2025-09-27 | $5,000-15,000 | Senior Engineer + Documentation Specialist | 100% Documentation Complete & Audit Ready | High | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
106 |  | analysis techniques, witness a typical titration or other test to confirm minimal skill levels in us... | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
107 |  | specifications/(PCD) are accounted for. Specification identified contaminant limits are concentratio... | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown | PLANNED
108 |  | addition calculations? Do internal procedures ensure tank samples are representative of a | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
109 |  | uniformity. Do the solution control records contain the following information for | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
110 |  | each tank monitored: Tank Identification? | Low | No | PARTIAL | Develop supporting documentation to address requirement | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low |  | PLANNED
111 |  | Tank Contents? | Low | No | PARTIAL | Develop supporting documentation to address requirement | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low |  | PLANNED
112 |  | Tank size (working volume) and level? | Low | No | PARTIAL | Develop supporting documentation to address requirement | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low |  | PLANNED
113 |  | Analysis frequency? | Low | No | PARTIAL | Develop supporting documentation to address requirement | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low |  | PLANNED
114 |  | Constituents to be analyzed and/or properties to be tested? | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
115 |  | rate, pH, conductivity, if that is how the solution is controlled. Etch rate for the purpose of dete... | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown | PLANNED
116 |  | example of a Solution Matrix which may be used as a tool to help meet this requirement. Date sampled... | Low | No | PARTIAL | Develop supporting documentation to address requirement | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low |  | PLANNED
117 |  | Analysis result (e.g. titration value, refractive index value) and | Low | No | PARTIAL | Develop supporting documentation to address requirement | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low |  | PLANNED
118 |  | constituent value, e.g. auto-titrator, or the analysis is subcontracted, then only the constituent v... | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown | PLANNED
119 |  | controls, for example- electroless nickel. Tank dumps? | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown | PLANNED
120 |  | Reanalysis after addition when out of specification limits? | Low | No | PARTIAL | Develop supporting documentation to address requirement | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low |  | PLANNED
121 |  | Identity of individual conducting analyzes, additions, reanalysis and | Low | No | PARTIAL | Develop supporting documentation to address requirement | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low |  | PLANNED
122 |  | dumps? Do solution control records demonstrate: | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
123 |  | Solution constituents/properties are analyzed/tested at the defined | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
124 |  | frequency? Solutions constituents/properties are maintained within | Low | No | PARTIAL | Develop supporting documentation to address requirement | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low |  | PLANNED
125 |  | is not an NCR against this question. The process is stopped when any constituent/property does not c... | Low | No | PARTIAL | Develop supporting documentation to address requirement | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low |  | PLANNED
126 |  | analysis indicated it likely went outside limits, check what was done to prevent hardware being proc... | Low | No | PARTIAL | Develop supporting documentation to address requirement | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low |  | PLANNED
127 |  | Are current operating manuals or instructions available to operators, | Low | No | PARTIAL | Develop supporting documentation to address requirement | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low |  | PLANNED
128 |  | Are maintenance procedures prepared with preventative maintenance | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
129 |  | downtime due to equipment failure. The facility maintenance program should include scheduled equipme... | Medium | Yes | PARTIAL | Review existing documentation to ensure full compliance | 60 | 2025-10-27 | $2,000-8,000 | Engineer + Documentation Support | 100% Documentation Complete & Audit Ready | Medium | Unknown; Unknown | PLANNED
130 |  | do not include tanks. Are tanks and/or work surfaces maintained free of corrosion and | Low | No | PARTIAL | Develop supporting documentation to address requirement | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low |  | PLANNED
131 |  | tanks. Clean, clear, free-running or monitored for contamination levels? | Low | No | PARTIAL | Develop supporting documentation to address requirement | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low |  | PLANNED
132 |  | provided afterward. Situated in a sequence to prevent cross contamination of process | Low | No | PARTIAL | Develop supporting documentation to address requirement | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low |  | PLANNED
133 |  | tanks? Assuring adequate neutralization and/or removal of process chemicals? | Low | No | PARTIAL | Develop supporting documentation to address requirement | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low |  | PLANNED
134 |  | Is there a system to ensure tanks with defined operating temperature | Low | No | PARTIAL | Develop supporting documentation to address requirement | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low |  | PLANNED
135 |  | tanks. The control and recording process needs to account for environmental temperature changes (sum... | High | Yes | PARTIAL | Review existing documentation to ensure full compliance | 30 | 2025-09-27 | $5,000-15,000 | Senior Engineer + Documentation Specialist | 100% Documentation Complete & Audit Ready | High | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
136 |  | tanks or if tank temperatures are recorded for every load. Objective evidence could be a record of t... | High | Yes | PARTIAL | Review existing documentation to ensure full compliance | 30 | 2025-09-27 | $5,000-15,000 | Senior Engineer + Documentation Specialist | 100% Documentation Complete & Audit Ready | High | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
137 |  | Is work electrically isolated from the electrical power supply of hoists | Low | No | PARTIAL | Develop supporting documentation to address requirement | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low |  | PLANNED
138 |  | equipment are used, electrically powered hoists or lifting equipment is disconnected during processi... | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown | PLANNED
139 |  | above 250°F (121°C). See Section 2.6 for the definition of Thermal Treatment. Part drying is not con... | High | Yes | PARTIAL | Review existing documentation to ensure full compliance | 30 | 2025-09-27 | $5,000-15,000 | Senior Engineer + Documentation Specialist | 100% Documentation Complete & Audit Ready | High | Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
140 |  | For each oven that operates at a set point above 250ºF (121ºC), does | Low | No | PARTIAL | Develop supporting documentation to address requirement | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low |  | PLANNED
141 |  | the Auditee identify: The oven ID? | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown | PLANNED
142 |  | The operating range? | Low | No | PARTIAL | Develop supporting documentation to address requirement | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low |  | PLANNED
143 |  | The uniformity requirement? | Low | No | PARTIAL | Develop supporting documentation to address requirement | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low |  | PLANNED
144 |  | The qualified working zone? | Low | No | PARTIAL | Develop supporting documentation to address requirement | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low |  | PLANNED
145 |  | thermocouples for the TUS. Parts must be placed within this zone. Does the defined operating range a... | High | No | PARTIAL | Develop supporting documentation to address requirement | 30 | 2025-09-27 | $5,000-15,000 | Senior Engineer + Documentation Specialist | 100% Documentation Complete & Audit Ready | High |  | PLANNED
146 |  | specification requirements for which the oven is used? Are parts only placed within the qualified wo... | Low | No | PARTIAL | Develop supporting documentation to address requirement | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low |  | PLANNED
147 |  | Does the oven have at least one temperature control sensor in each | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown | PLANNED
148 |  | control zone, attached to a control instrument that controls and displays temperature? Does the oven... | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
149 |  | temperature and time for each control zone? Does the oven have over-temperature protection in each c... | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown | PLANNED
150 |  | Are instrument (temperature controller, overtemperature controller, time | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown | PLANNED
151 |  | and temperature recorder) calibrations performed in accordance with, or certified to, AMS2750? For d... | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
152 |  | 1.1°C), or ±1°C if the instrument only displays whole numbers, or ±0.2% of the test temperature read... | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
153 |  | Are temperature instrument calibration frequencies at least semi- | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
154 |  | annually for digital instruments and quarterly for analogue instruments? Is the timing function for ... | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown | PLANNED
155 |  | are not used. Is the timing function for all digital recording instruments and data | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown | PLANNED
156 |  | are not used. Are chart recorder (circular and strip) speed(s) calibrated/verified at | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown | PLANNED
157 |  | Is resolution of the chart recorder equal to or better than ±10ºF (±6ºC)? | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown | PLANNED
158 |  | Are system accuracy tests (SATs) performed in accordance with, or | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
159 |  | Was a SAT performed after any maintenance that could affect the SAT | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown | PLANNED
160 |  | calibration of the instrument when any adjustment has been made. Are SATs performed bi-weekly, or le... | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
161 |  | to requirements if less frequent SATs are performed. If an oven is used infrequently at a set point ... | Low | No | PARTIAL | Develop supporting documentation to address requirement | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low |  | PLANNED
162 |  | the test temperature, whichever is greater? Are temperature uniformity surveys (TUSs) performed in a... | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
163 |  | with, or certified to, AMS2750? If the highest and lowest test temperatures are more than 600°F | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
164 |  | F (or 335°C). Over a period of 12 months, are TUSs performed at the minimum and | Low | No | PARTIAL | Develop supporting documentation to address requirement | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low |  | PLANNED
165 |  | TUS at that set point. Are TUSs performed at least quarterly, or less frequently if the oven | Low | No | PARTIAL | Develop supporting documentation to address requirement | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low |  | PLANNED
166 |  | to requirements if less frequent TUSs are performed. Do TUS results demonstrate the uniformity meets... | Low | No | PARTIAL | Develop supporting documentation to address requirement | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low |  | PLANNED
167 |  | 135-149°C) then this is considered the allowed set point range. Does the Auditee have a procedure/in... | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
168 |  | 121ºC) or other miscellaneous heating processes are performed within the scope of the audit or if th... | High | Yes | PARTIAL | Review existing documentation to ensure full compliance | 30 | 2025-09-27 | $5,000-15,000 | Senior Engineer + Documentation Specialist | 100% Documentation Complete & Audit Ready | High | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
169 |  | to provide the required temperature without the use of a temperature controller. Do procedures requi... | High | Yes | PARTIAL | Review existing documentation to ensure full compliance | 30 | 2025-09-27 | $5,000-15,000 | Senior Engineer + Documentation Specialist | 100% Documentation Complete & Audit Ready | High | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
170 |  | scope of the audit. Do chemical stripping baths include an inhibiting agent when required | High | Yes | PARTIAL | Review existing documentation to ensure full compliance | 30 | 2025-09-27 | $5,000-15,000 | Senior Engineer + Documentation Specialist | 100% Documentation Complete & Audit Ready | High | Unknown | PLANNED
171 |  | Does the hardware receive an embrittlement relief bake after chemical | Low | No | PARTIAL | Develop supporting documentation to address requirement | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low |  | PLANNED
172 |  | or when chemical stripping is not performed. Are masking, insulators, or similar methods being used ... | Low | No | PARTIAL | Develop supporting documentation to address requirement | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low |  | PLANNED
173 |  | no dissimilar metal couples. If required by the customer, has the stripping of parts and the process | High | No | PARTIAL | Develop supporting documentation to address requirement | 30 | 2025-09-27 | $5,000-15,000 | Senior Engineer + Documentation Specialist | 100% Documentation Complete & Audit Ready | High |  | PLANNED
174 |  | For each strip cycle, are all stripping operations appropriately planned, | Low | No | PARTIAL | Develop supporting documentation to address requirement | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low |  | PLANNED
175 |  | processing documented, and traceable to the hardware? When stripping is not part of the standard pro... | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown | PLANNED
176 |  | nonconformance after plating/ coating. NA applies if stripping is the expectation of the customer as... | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
177 |  | Do strip procedures include an inspection of the stripped component | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
178 |  | Do the lot inspection and lot test procedures require sufficient data to | Low | Yes | PARTIAL | Review existing documentation to ensure full compliance | 90 | 2025-11-26 | $1,000-5,000 | Documentation Specialist | 100% Documentation Complete & Audit Ready | Low | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED

## Executive_Summary
Value
Total_Actions_Required | 178
High_Priority_Actions | 23
Medium_Priority_Actions | 1
Low_Priority_Actions | 154
Total_NADCAP_Clauses | 178
Gaps_Identified | 0
Partial_Coverage | 0
Target_Completion | 2025-11-26
Estimated_Total_Cost | $50,000-200,000
Generated_Date | 2025-08-28 12:23:02

## Priority_Breakdown
Count
Low | 154
High | 23
Medium | 1

## High_Priority_Focus
Action_ID | NADCAP_Clause | Requirement_Description | Priority | Current_Coverage | Gap_Identified | Recommended_Action | Timeline_Days | Due_Date | Estimated_Cost | Resource_Requirements | Success_Criteria | Risk_Level | Existing_Documents | Implementation_Status
2 |  | Has the Auditee identified what chemical process scope data shall be | High | Yes | PARTIAL | Review existing documentation to ensure full compliance | 30 | 2025-09-27 | $5,000-15,000 | Senior Engineer + Documentation Specialist | 100% Documentation Complete & Audit Ready | High | Unknown | PLANNED
12 |  | Does shop paper/traveler, which accompanies each lot, contain as a minimum the following information... | High | No | PARTIAL | Develop supporting documentation to address requirement | 30 | 2025-09-27 | $5,000-15,000 | Senior Engineer + Documentation Specialist | 100% Documentation Complete & Audit Ready | High |  | PLANNED
13 |  | Operations defined by the customer as non-critical or non-technical may be exempt from approval requ... | High | No | PARTIAL | Develop supporting documentation to address requirement | 30 | 2025-09-27 | $5,000-15,000 | Senior Engineer + Documentation Specialist | 100% Documentation Complete & Audit Ready | High |  | PLANNED
14 |  | contract number, but must have traceability to it, or to the engineering requirements. Part identifi... | High | No | PARTIAL | Develop supporting documentation to address requirement | 30 | 2025-09-27 | $5,000-15,000 | Senior Engineer + Documentation Specialist | 100% Documentation Complete & Audit Ready | High |  | PLANNED
15 |  | traveler unless one of the following applies: it does not influence the process steps/sequence; when... | High | Yes | PARTIAL | Review existing documentation to ensure full compliance | 30 | 2025-09-27 | $5,000-15,000 | Senior Engineer + Documentation Specialist | 100% Documentation Complete & Audit Ready | High | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
16 |  | jobs audited. Type may be substituted by material and size. Reference to a defined Test Piece, e.g. ... | High | Yes | PARTIAL | Review existing documentation to ensure full compliance | 30 | 2025-09-27 | $5,000-15,000 | Senior Engineer + Documentation Specialist | 100% Documentation Complete & Audit Ready | High | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
22 | 3.6.1.5.6 | audited. Shop paper to reference internal racking instruction, a general instruction for routine rac... | High | Yes | PARTIAL | Review existing documentation to ensure full compliance | 30 | 2025-09-27 | $5,000-15,000 | Senior Engineer + Documentation Specialist | 100% Documentation Complete & Audit Ready | High | Unknown | PLANNED
41 |  | PCD must comply with applicable specification or customer requirements. The traveler may define tigh... | High | Yes | PARTIAL | Review existing documentation to ensure full compliance | 30 | 2025-09-27 | $5,000-15,000 | Senior Engineer + Documentation Specialist | 100% Documentation Complete & Audit Ready | High | Unknown; Unknown; Unknown | PLANNED
49 |  | are not contractually required. Actual pre-process dimensions may be provided by earlier machining i... | High | Yes | PARTIAL | Review existing documentation to ensure full compliance | 30 | 2025-09-27 | $5,000-15,000 | Senior Engineer + Documentation Specialist | 100% Documentation Complete & Audit Ready | High | Unknown; Unknown; Unknown; Unknown | PLANNED
57 |  | affecting hardware? (i.e. out of tolerance conditions) Is rework approved by the customer when requi... | High | No | PARTIAL | Develop supporting documentation to address requirement | 30 | 2025-09-27 | $5,000-15,000 | Senior Engineer + Documentation Specialist | 100% Documentation Complete & Audit Ready | High |  | PLANNED
66 |  | calibration cover the range of use and the required instrument accuracy? For instruments used to con... | High | Yes | PARTIAL | Review existing documentation to ensure full compliance | 30 | 2025-09-27 | $5,000-15,000 | Senior Engineer + Documentation Specialist | 100% Documentation Complete & Audit Ready | High | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
67 |  | accordance with the relevant section of AC7108/4 Appendix B. Where Appendix B does not have an appli... | High | Yes | PARTIAL | Review existing documentation to ensure full compliance | 30 | 2025-09-27 | $5,000-15,000 | Senior Engineer + Documentation Specialist | 100% Documentation Complete & Audit Ready | High | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
70 |  | Periodic testing shall be audited in accordance with the relevant section of AC7108/4 Appendix B. Wh... | High | Yes | PARTIAL | Review existing documentation to ensure full compliance | 30 | 2025-09-27 | $5,000-15,000 | Senior Engineer + Documentation Specialist | 100% Documentation Complete & Audit Ready | High | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
76 |  | must be available monthly. The Auditee must not retain processed test pieces for several periods and... | High | Yes | PARTIAL | Review existing documentation to ensure full compliance | 30 | 2025-09-27 | $5,000-15,000 | Senior Engineer + Documentation Specialist | 100% Documentation Complete & Audit Ready | High | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
105 |  | results, authorization of re-analysis, calculation of process solution additions and corrections, an... | High | Yes | PARTIAL | Review existing documentation to ensure full compliance | 30 | 2025-09-27 | $5,000-15,000 | Senior Engineer + Documentation Specialist | 100% Documentation Complete & Audit Ready | High | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
135 |  | tanks. The control and recording process needs to account for environmental temperature changes (sum... | High | Yes | PARTIAL | Review existing documentation to ensure full compliance | 30 | 2025-09-27 | $5,000-15,000 | Senior Engineer + Documentation Specialist | 100% Documentation Complete & Audit Ready | High | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
136 |  | tanks or if tank temperatures are recorded for every load. Objective evidence could be a record of t... | High | Yes | PARTIAL | Review existing documentation to ensure full compliance | 30 | 2025-09-27 | $5,000-15,000 | Senior Engineer + Documentation Specialist | 100% Documentation Complete & Audit Ready | High | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
139 |  | above 250°F (121°C). See Section 2.6 for the definition of Thermal Treatment. Part drying is not con... | High | Yes | PARTIAL | Review existing documentation to ensure full compliance | 30 | 2025-09-27 | $5,000-15,000 | Senior Engineer + Documentation Specialist | 100% Documentation Complete & Audit Ready | High | Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
145 |  | thermocouples for the TUS. Parts must be placed within this zone. Does the defined operating range a... | High | No | PARTIAL | Develop supporting documentation to address requirement | 30 | 2025-09-27 | $5,000-15,000 | Senior Engineer + Documentation Specialist | 100% Documentation Complete & Audit Ready | High |  | PLANNED
168 |  | 121ºC) or other miscellaneous heating processes are performed within the scope of the audit or if th... | High | Yes | PARTIAL | Review existing documentation to ensure full compliance | 30 | 2025-09-27 | $5,000-15,000 | Senior Engineer + Documentation Specialist | 100% Documentation Complete & Audit Ready | High | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
169 |  | to provide the required temperature without the use of a temperature controller. Do procedures requi... | High | Yes | PARTIAL | Review existing documentation to ensure full compliance | 30 | 2025-09-27 | $5,000-15,000 | Senior Engineer + Documentation Specialist | 100% Documentation Complete & Audit Ready | High | Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown; Unknown | PLANNED
170 |  | scope of the audit. Do chemical stripping baths include an inhibiting agent when required | High | Yes | PARTIAL | Review existing documentation to ensure full compliance | 30 | 2025-09-27 | $5,000-15,000 | Senior Engineer + Documentation Specialist | 100% Documentation Complete & Audit Ready | High | Unknown | PLANNED
173 |  | no dissimilar metal couples. If required by the customer, has the stripping of parts and the process | High | No | PARTIAL | Develop supporting documentation to address requirement | 30 | 2025-09-27 | $5,000-15,000 | Senior Engineer + Documentation Specialist | 100% Documentation Complete & Audit Ready | High |  | PLANNED