## Slide 1
SAFRAN
REACh Program
Milestone Dashboard: Documentation & Training
Milestones for this month
Milestone | Date | Status
ZnNi Line SOPs - Final Review | 15-Aug-25 | In Progress
Training Materials Complete | 18-Aug-25 | Planned
Documentation QA Review | 12-Aug-25 | Complete
Process Validation Sign-off | 20-Aug-25 | Planned
Operator Certification Ready | 25-Aug-25 | Planned
Risks for Documentation and Training
Risk | Impact | Mitigation
Documentation delays due to SME availability | Medium | Scheduled dedicated review sessions
Training material complexity | Low | Simplified modules with visual aids
Version control issues | High | Centralized document management system
Milestones planned for next month
Milestone | Date | Status
Operator Certification Program | 08-Sep-25 | Planned
Advanced Training Module | 15-Sep-25 | Planned
Documentation Review Cycle | 22-Sep-25 | Planned
Milestones completed last month
Milestone | Date | Status
Emergency Procedures Sign-off | 28-Jul-25 | Complete
Training Program Phase 1 | 30-Jul-25 | Complete
Documentation Standards v1.0 | 25-Jul-25 | Complete